# Memoirs Strategy Document

# 🎯 Vision

To preserve and share the untold stories, wisdom, and lived experiences of elderly people and public figures for posterity, inspiration, and learning.

# Mission

To build an engaging content platform that documents rich life stories through authentic, high-quality video storytelling and grows into a repository of wisdom and human history.

# Core Objectives

Launch a compelling, high-quality video podcast series.

Build an engaged YouTube and social media audience.

Evolve into a documentary series aired on streaming platforms.

Host a live storytelling/launch event for community engagement.

Monetize through content licensing, sponsorships, merchandise, and digital distribution.

# Target Audience

Millennials and Gen Z interested in history, culture, and legacy

Diaspora communities seeking cultural reconnection

Researchers, journalists, students, and content lovers

Families looking to preserve their own legacies

# 📅 Work Plan (Phase by Phase)

## Phase 1: Development (Month 1)

Finalize branding, visual identity, theme song, and intro

Secure first 6 guests (mix of elderly and public figures)

Acquire/arrange filming equipment and studio setup

Build production team: Director, Cinematographer, Editor, Producer

Design YouTube channel and social platforms

## Phase 2: Production (Month 2-3)

Film and edit the first 6–10 episodes

Create promotional assets (thumbnails, teaser reels, trailers)

Develop intro video, episode format, and storytelling arc

Create a branded 'Memoirs Journal' for documentation

## Phase 3: Launch & Distribution (Month 4)

Launch Memoirs YouTube channel and first 3 episodes

Weekly episode drop (YouTube + Spotify + Apple Podcasts)

Email newsletter campaign with story excerpts

Strategic guest rollout to grow audience via their networks

## Phase 4: Growth & Partnerships (Month 5–9)

Collaborate with legacy NGOs, embassies, cultural ministries

Begin shooting “Memoirs: The Documentary Series” (longer format)

Host “Memoirs Live” event (recorded public storytelling event)

Explore distribution partnerships with Netflix, Amazon, EbonyLife, etc.